## Cover & Instructions
CHAK Monthly Project Performance Monitoring Template
Financial performance (burn rate & Budget vs. Actual) combined with technical/donor indicator performance — across all 10 CHAK project portfolios: Jamii Tekelezi, CHAP Stawisha, Eye Health - ACSP & GitLab, EIS, BFTW HSS, BFTW RMNCAH, PEP, GF-MNCH, IMPACT and CDIC-iCARE.
HOW TO USE THIS WORKBOOK
1. Each of the 10 project tabs has the same structure: project header (donor, project code, reporting month/period, duration, months elapsed), Section A — Financial Performance (9 budget lines + a Total Project Budget row), Section B — Technical/Donor Indicator Performance (8 indicators), and Section C — Overall Project Health (Financial RAG, Technical RAG, and a combined Overall RAG).
2. Enter blue-font cells only — these are inputs (annual budget per line, project duration, months elapsed, actual cumulative expenditure, current-month spend, annual target per indicator, actual cumulative result). Black-font cells are formulas — do not overtype them. Green-font cells link from another tab (Portfolio Dashboard only).
3. "Months Elapsed" and "Project Duration (months)" drive the linear planned (expected) cumulative budget and target for every budget line and indicator — adjust the planned-progress formula if a project's spend or target profile is not even/straight-line across the year.
4. RAG status is automatic. Financial: variance within ±10% of planned cumulative spend = On Track, ±10-20% = Watch, beyond ±20% = Off Track (both over- and under-spend are flagged, since underspend signals an absorption/refund risk). Technical: achievement ≥90% of planned cumulative target = On Track, 75-89% = Watch, below 75% = Off Track. Section C combines both: Financial RAG (from the Total Project Budget row), Technical RAG (the worst rating among the 8 indicators), and Overall Project Health (the worst of the two).
5. The Portfolio Dashboard tab pulls live figures from all 10 project tabs — including each project's Financial RAG, Technical RAG, indicators-off-track count and Overall RAG — and rolls them up into a CEO Snapshot (counts of On Track / Watch / Off Track projects and overall budget utilisation). Refresh it after updating any project tab; no manual entry is needed there.
6. Update this workbook once a month, after the reporting month closes, using actual cumulative expenditure and indicator results from finance and M&E records for each project.
7. Indicator names, donor names and project codes shown are illustrative placeholders — replace them with each project's specific donor M&E framework indicators, definitions, reporting frequency, and contractual donor/code details where they differ.
COLOR KEY
Blue text | Input cell — edit this
Black text | Formula — do not edit
Green text | Link pulling from another tab
On Track
Watch
Off Track

## Portfolio Dashboard
CHAK Project Portfolio — Monthly Health Dashboard
Auto-populated from each project tab — refresh after updating any project's monthly data.
Project | Donor | Total Annual Budget | Cumulative Expenditure | Budget Variance (%) | Financial RAG | Technical RAG | Indicators Off Track | Overall RAG
Jamii Tekelezi | US - DOS | 68500000 | 36755000 | 7.314% | Watch | Off Track | 1 of 8 | Off Track
CHAP Stawisha | CDC | 0 | 0 | N/A | N/A | Off Track | 1 of 8 | Off Track
Eye Health - ACSP & GitLab | ACHAP / GitLab Foundation | 68500000 | 25687500 | -10% | On Track | On Track | 0 of 8 | On Track
EIS | Bill & Melinda Gates Foundation | 68500000 | 35677084 | 25% | Off Track | Off Track | 8 of 8 | Off Track
BFTW HSS | Bread for the World | 68500000 | 27685416 | -3% | On Track | Watch | 0 of 8 | Watch
BFTW RMNCAH | Bread for the World | 68500000 | 29968750 | 5% | On Track | On Track | 0 of 8 | On Track
PEP | Novo Nordisk Foundation (NNF) | 68500000 | 11873334 | -22% | Off Track | On Track | 0 of 8 | Off Track
GF-MNCH | Bill & Melinda Gates Foundation | 68500000 | 34592500 | 1% | On Track | On Track | 0 of 8 | On Track
IMPACT | action medeor | 68500000 | 51945834 | 30% | Off Track | Off Track | 8 of 8 | Off Track
CDIC-iCARE | CDC / iCARE | 68500000 | 24660000 | 8% | On Track | Watch | 0 of 8 | Watch
PORTFOLIO TOTAL |  | 616500000 | 278845418 | See project tabs for planned-vs-actual detail
CEO SNAPSHOT — PORTFOLIO STATUS AT A GLANCE
Projects On Track (Overall RAG): |  | 3 of 10 | Projects on Watch: |  | 2 of 10
Projects Off Track (Overall RAG): |  | 5 of 10 | Portfolio Budget Utilisation: |  | 45.23%
RAG LEGEND: On Track = within tolerance · Watch = approaching threshold, needs attention · Off Track = requires corrective action

## Jamii Tekelezi
Jamii Tekelezi Monthly Performance Monitoring
Donor: | US - DOS |  | Reporting Month: |  | 2026-06-29 |  | Project Duration (months): |  | 12
Project Code: | CHAK/2026/01 |  | Reporting Period: |  | Type reporting period here... |  | Months Elapsed to Date: |  | 6
SECTION A · FINANCIAL PERFORMANCE — BURN RATE & BUDGET VS. ACTUAL (BVA)
Budget Line | Annual Budget | Planned Cumulative Budget to Date | Actual Cumulative Expenditure to Date | Variance ($) | Variance (%) | Current Month Expenditure | Avg. Monthly Burn Rate | Projected Annual Expenditure | Months Remaining | RAG
Personnel & HR | 18000000 | 9000000 | 11000000 | 2000000 | 22.22% | 1530000 | 1833333.3333 | 22000000 | 6 | Off Track
Technical / Program Activities | 9000000 | 4500000 | 4590000 | 90000 | 2% | 765000 | 765000 | 9180000 | 6 | On Track
Equipment, Supplies & Commodities | 7500000 | 3750000 | 3825000 | 75000 | 2% | 637500 | 637500 | 7650000 | 6 | On Track
Training & Capacity Building | 6000000 | 3000000 | 3060000 | 60000 | 2% | 510000 | 510000 | 6120000 | 6 | On Track
Sub-awards / Partner Disbursements | 9500000 | 4750000 | 4845000 | 95000 | 2% | 807500 | 807500 | 9690000 | 6 | On Track
Monitoring, Evaluation & Learning | 4000000 | 2000000 | 2040000 | 40000 | 2% | 340000 | 340000 | 4080000 | 6 | On Track
Travel & Transport | 6500000 | 3250000 | 3315000 | 65000 | 2% | 552500 | 552500 | 6630000 | 6 | On Track
Administration & Overheads | 3000000 | 1500000 | 1530000 | 30000 | 2% | 255000 | 255000 | 3060000 | 6 | On Track
Other Direct Costs / Contingency | 5000000 | 2500000 | 2550000 | 50000 | 2% | 425000 | 425000 | 5100000 | 6 | On Track
TOTAL PROJECT BUDGET | 68500000 | 34250000 | 36755000 | 2505000 | 7.314% | 5822500 | 6125833.3333 | 73510000 | 6 | Watch
Planned cumulative budget assumes even (straight-line) spend across the project duration. Variance >20% in either direction triggers Off Track — overspend risks a funding gap; underspend risks an end-of-award absorption/refund issue.
SECTION B · TECHNICAL / DONOR INDICATOR PERFORMANCE
Indicator | Unit / Definition | Annual Target | Planned Cumulative Target to Date | Actual Cumulative Result to Date | Achievement (%) |  |  |  |  | RAG
Tracer Indicator 1 | Define per donor M&E framework | 1200 | 600 | 400 | 66.67% |  |  |  |  | Off Track
Tracer Indicator 2 | Define per donor M&E framework | 600 | 300 | 250 | 83.33% |  |  |  |  | Watch
Tracer Indicator 3 | Define per donor M&E framework | 900 | 450 | 428 | 95.11% |  |  |  |  | On Track
Tracer Indicator 4 | Define per donor M&E framework | 450 | 225 | 214 | 95.11% |  |  |  |  | On Track
Tracer Indicator 5 | Define per donor M&E framework | 1500 | 750 | 712 | 94.93% |  |  |  |  | On Track
Tracer Indicator 6 | Define per donor M&E framework | 300 | 150 | 142 | 94.67% |  |  |  |  | On Track
Tracer Indicator 7 | Define per donor M&E framework | 750 | 375 | 356 | 94.93% |  |  |  |  | On Track
Tracer Indicator 8 | Define per donor M&E framework | 200 | 100 | 95 | 95% |  |  |  |  | On Track
Indicator names are standard/illustrative donor indicators for this project type — replace with your specific donor's exact indicator list, definitions and reporting frequency where they differ.
SECTION C · OVERALL PROJECT HEALTH
Financial RAG (Total Budget): |  |  | Watch | Off-Track Budget Lines: |  |  |  | 1 of 9
Technical RAG (Indicator Performance): |  |  | Off Track | Off-Track Indicators: |  |  |  | 1 of 8
OVERALL PROJECT HEALTH: |  |  | Off Track
Programme Manager's Narrative — key achievements, bottlenecks, and corrective actions this month:
Type narrative here...

## CHAP Stawisha
CHAP Stawisha Monthly Performance Monitoring
Donor: | CDC |  | Reporting Month: |  | 2026-06-29 |  | Project Duration (months): |  | 12
Project Code: | CHAK/2026/02 |  | Reporting Period: |  | Type reporting period here... |  | Months Elapsed to Date: |  | 6
SECTION A · FINANCIAL PERFORMANCE — BURN RATE & BUDGET VS. ACTUAL (BVA)
Budget Line | Annual Budget | Planned Cumulative Budget to Date | Actual Cumulative Expenditure to Date | Variance ($) | Variance (%) | Current Month Expenditure | Avg. Monthly Burn Rate | Projected Annual Expenditure | Months Remaining | RAG
Personnel & HR |  | 0 |  | 0 | N/A |  | 0 | N/A | 6 | N/A
Technical / Program Activities |  | 0 |  | 0 | N/A |  | 0 | N/A | 6 | N/A
Equipment, Supplies & Commodities |  | 0 |  | 0 | N/A |  | 0 | N/A | 6 | N/A
Training & Capacity Building |  | 0 |  | 0 | N/A |  | 0 | N/A | 6 | N/A
Sub-awards / Partner Disbursements |  | 0 |  | 0 | N/A |  | 0 | N/A | 6 | N/A
Monitoring, Evaluation & Learning |  | 0 |  | 0 | N/A |  | 0 | N/A | 6 | N/A
Travel & Transport |  | 0 |  | 0 | N/A |  | 0 | N/A | 6 | N/A
Administration & Overheads |  | 0 |  | 0 | N/A |  | 0 | N/A | 6 | N/A
Other Direct Costs / Contingency |  | 0 |  | 0 | N/A |  | 0 | N/A | 6 | N/A
TOTAL PROJECT BUDGET | 0 | 0 | 0 | 0 | N/A | 0 | 0 | N/A | 6 | N/A
Planned cumulative budget assumes even (straight-line) spend across the project duration. Variance >20% in either direction triggers Off Track — overspend risks a funding gap; underspend risks an end-of-award absorption/refund issue.
SECTION B · TECHNICAL / DONOR INDICATOR PERFORMANCE
Indicator | Unit / Definition | Annual Target | Planned Cumulative Target to Date | Actual Cumulative Result to Date | Achievement (%) |  |  |  |  | RAG
Tracer Indicator 1 | Define per donor M&E framework | 500 | 250 | 125 | 50% |  |  |  |  | Off Track
Tracer Indicator 2 | Define per donor M&E framework |  | 0 |  | N/A |  |  |  |  | N/A
Tracer Indicator 3 | Define per donor M&E framework |  | 0 |  | N/A |  |  |  |  | N/A
Tracer Indicator 4 | Define per donor M&E framework |  | 0 |  | N/A |  |  |  |  | N/A
Tracer Indicator 5 | Define per donor M&E framework |  | 0 |  | N/A |  |  |  |  | N/A
Tracer Indicator 6 | Define per donor M&E framework |  | 0 |  | N/A |  |  |  |  | N/A
Tracer Indicator 7 | Define per donor M&E framework |  | 0 |  | N/A |  |  |  |  | N/A
Tracer Indicator 8 | Define per donor M&E framework |  | 0 |  | N/A |  |  |  |  | N/A
Indicator names are standard/illustrative donor indicators for this project type — replace with your specific donor's exact indicator list, definitions and reporting frequency where they differ.
SECTION C · OVERALL PROJECT HEALTH
Financial RAG (Total Budget): |  |  | N/A | Off-Track Budget Lines: |  |  |  | 0 of 9
Technical RAG (Indicator Performance): |  |  | Off Track | Off-Track Indicators: |  |  |  | 1 of 8
OVERALL PROJECT HEALTH: |  |  | Off Track
Programme Manager's Narrative — key achievements, bottlenecks, and corrective actions this month:
Type narrative here...

## Eye Health - ACSP & GitLab
Eye Health (ACSP & GitLab Foundation) Monthly Performance Monitoring
Donor: | ACHAP / GitLab Foundation |  | Reporting Month: |  | 2026-06-29 |  | Project Duration (months): |  | 12
Project Code: | CHAK/2026/03 |  | Reporting Period: |  | Type reporting period here... |  | Months Elapsed to Date: |  | 5
SECTION A · FINANCIAL PERFORMANCE — BURN RATE & BUDGET VS. ACTUAL (BVA)
Budget Line | Annual Budget | Planned Cumulative Budget to Date | Actual Cumulative Expenditure to Date | Variance ($) | Variance (%) | Current Month Expenditure | Avg. Monthly Burn Rate | Projected Annual Expenditure | Months Remaining | RAG
Personnel & HR | 18000000 | 7500000 | 6750000 | -750000 | -10% | 1350000 | 1350000 | 16200000 | 7 | On Track
Technical / Program Activities | 9000000 | 3750000 | 3375000 | -375000 | -10% | 675000 | 675000 | 8100000 | 7 | On Track
Equipment, Supplies & Commodities | 7500000 | 3125000 | 2812500 | -312500 | -10% | 562500 | 562500 | 6750000 | 7 | On Track
Training & Capacity Building | 6000000 | 2500000 | 2250000 | -250000 | -10% | 450000 | 450000 | 5400000 | 7 | On Track
Sub-awards / Partner Disbursements | 9500000 | 3958333.3333 | 3562500 | -395833.3333 | -10% | 712500 | 712500 | 8550000 | 7 | On Track
Monitoring, Evaluation & Learning | 4000000 | 1666666.6667 | 1500000 | -166666.6667 | -10% | 300000 | 300000 | 3600000 | 7 | On Track
Travel & Transport | 6500000 | 2708333.3333 | 2437500 | -270833.3333 | -10% | 487500 | 487500 | 5850000 | 7 | On Track
Administration & Overheads | 3000000 | 1250000 | 1125000 | -125000 | -10% | 225000 | 225000 | 2700000 | 7 | On Track
Other Direct Costs / Contingency | 5000000 | 2083333.3333 | 1875000 | -208333.3333 | -10% | 375000 | 375000 | 4500000 | 7 | On Track
TOTAL PROJECT BUDGET | 68500000 | 28541666.6667 | 25687500 | -2854166.6667 | -10% | 5137500 | 5137500 | 61650000 | 7 | On Track
Planned cumulative budget assumes even (straight-line) spend across the project duration. Variance >20% in either direction triggers Off Track — overspend risks a funding gap; underspend risks an end-of-award absorption/refund issue.
SECTION B · TECHNICAL / DONOR INDICATOR PERFORMANCE
Indicator | Unit / Definition | Annual Target | Planned Cumulative Target to Date | Actual Cumulative Result to Date | Achievement (%) |  |  |  |  | RAG
Tracer Indicator 1 | Define per donor M&E framework | 1200 | 500 | 460 | 92% |  |  |  |  | On Track
Tracer Indicator 2 | Define per donor M&E framework | 600 | 250 | 230 | 92% |  |  |  |  | On Track
Tracer Indicator 3 | Define per donor M&E framework | 900 | 375 | 345 | 92% |  |  |  |  | On Track
Tracer Indicator 4 | Define per donor M&E framework | 450 | 187.5 | 172 | 91.73% |  |  |  |  | On Track
Tracer Indicator 5 | Define per donor M&E framework | 1500 | 625 | 575 | 92% |  |  |  |  | On Track
Tracer Indicator 6 | Define per donor M&E framework | 300 | 125 | 115 | 92% |  |  |  |  | On Track
Tracer Indicator 7 | Define per donor M&E framework | 750 | 312.5 | 288 | 92.16% |  |  |  |  | On Track
Tracer Indicator 8 | Define per donor M&E framework | 200 | 83.3333 | 77 | 92.4% |  |  |  |  | On Track
Indicator names are standard/illustrative donor indicators for this project type — replace with your specific donor's exact indicator list, definitions and reporting frequency where they differ.
SECTION C · OVERALL PROJECT HEALTH
Financial RAG (Total Budget): |  |  | On Track | Off-Track Budget Lines: |  |  |  | 0 of 9
Technical RAG (Indicator Performance): |  |  | On Track | Off-Track Indicators: |  |  |  | 0 of 8
OVERALL PROJECT HEALTH: |  |  | On Track
Programme Manager's Narrative — key achievements, bottlenecks, and corrective actions this month:
Type narrative here...

## EIS
Evaluation of Integrated Services (EIS) Monthly Performance Monitoring
Donor: | Bill & Melinda Gates Foundation |  | Reporting Month: |  | 2026-06-29 |  | Project Duration (months): |  | 24
Project Code: | CHAK/2026/04 |  | Reporting Period: |  | Type reporting period here... |  | Months Elapsed to Date: |  | 10
SECTION A · FINANCIAL PERFORMANCE — BURN RATE & BUDGET VS. ACTUAL (BVA)
Budget Line | Annual Budget | Planned Cumulative Budget to Date | Actual Cumulative Expenditure to Date | Variance ($) | Variance (%) | Current Month Expenditure | Avg. Monthly Burn Rate | Projected Annual Expenditure | Months Remaining | RAG
Personnel & HR | 18000000 | 7500000 | 9375000 | 1875000 | 25% | 937500 | 937500 | 22500000 | 14 | Off Track
Technical / Program Activities | 9000000 | 3750000 | 4687500 | 937500 | 25% | 468750 | 468750 | 11250000 | 14 | Off Track
Equipment, Supplies & Commodities | 7500000 | 3125000 | 3906250 | 781250 | 25% | 390625 | 390625 | 9375000 | 14 | Off Track
Training & Capacity Building | 6000000 | 2500000 | 3125000 | 625000 | 25% | 312500 | 312500 | 7500000 | 14 | Off Track
Sub-awards / Partner Disbursements | 9500000 | 3958333.3333 | 4947917 | 989583.6667 | 25% | 494792 | 494791.7 | 11875000.8 | 14 | Off Track
Monitoring, Evaluation & Learning | 4000000 | 1666666.6667 | 2083333 | 416666.3333 | 25% | 208333 | 208333.3 | 4999999.2 | 14 | Off Track
Travel & Transport | 6500000 | 2708333.3333 | 3385417 | 677083.6667 | 25% | 338542 | 338541.7 | 8125000.8 | 14 | Off Track
Administration & Overheads | 3000000 | 1250000 | 1562500 | 312500 | 25% | 156250 | 156250 | 3750000 | 14 | Off Track
Other Direct Costs / Contingency | 5000000 | 2083333.3333 | 2604167 | 520833.6667 | 25% | 260417 | 260416.7 | 6250000.8 | 14 | Off Track
TOTAL PROJECT BUDGET | 68500000 | 28541666.6667 | 35677084 | 7135417.3333 | 25% | 3567709 | 3567708.4 | 85625001.6 | 14 | Off Track
Planned cumulative budget assumes even (straight-line) spend across the project duration. Variance >20% in either direction triggers Off Track — overspend risks a funding gap; underspend risks an end-of-award absorption/refund issue.
SECTION B · TECHNICAL / DONOR INDICATOR PERFORMANCE
Indicator | Unit / Definition | Annual Target | Planned Cumulative Target to Date | Actual Cumulative Result to Date | Achievement (%) |  |  |  |  | RAG
Tracer Indicator 1 | Define per donor M&E framework | 1200 | 500 | 350 | 70% |  |  |  |  | Off Track
Tracer Indicator 2 | Define per donor M&E framework | 600 | 250 | 175 | 70% |  |  |  |  | Off Track
Tracer Indicator 3 | Define per donor M&E framework | 900 | 375 | 262 | 69.87% |  |  |  |  | Off Track
Tracer Indicator 4 | Define per donor M&E framework | 450 | 187.5 | 131 | 69.87% |  |  |  |  | Off Track
Tracer Indicator 5 | Define per donor M&E framework | 1500 | 625 | 438 | 70.08% |  |  |  |  | Off Track
Tracer Indicator 6 | Define per donor M&E framework | 300 | 125 | 88 | 70.4% |  |  |  |  | Off Track
Tracer Indicator 7 | Define per donor M&E framework | 750 | 312.5 | 219 | 70.08% |  |  |  |  | Off Track
Tracer Indicator 8 | Define per donor M&E framework | 200 | 83.3333 | 58 | 69.6% |  |  |  |  | Off Track
Indicator names are standard/illustrative donor indicators for this project type — replace with your specific donor's exact indicator list, definitions and reporting frequency where they differ.
SECTION C · OVERALL PROJECT HEALTH
Financial RAG (Total Budget): |  |  | Off Track | Off-Track Budget Lines: |  |  |  | 9 of 9
Technical RAG (Indicator Performance): |  |  | Off Track | Off-Track Indicators: |  |  |  | 8 of 8
OVERALL PROJECT HEALTH: |  |  | Off Track
Programme Manager's Narrative — key achievements, bottlenecks, and corrective actions this month:
Type narrative here...

## BFTW HSS
BFTW - HSS Monthly Performance Monitoring
Donor: | Bread for the World |  | Reporting Month: |  | 2026-06-29 |  | Project Duration (months): |  | 12
Project Code: | CHAK/2026/05 |  | Reporting Period: |  | Type reporting period here... |  | Months Elapsed to Date: |  | 5
SECTION A · FINANCIAL PERFORMANCE — BURN RATE & BUDGET VS. ACTUAL (BVA)
Budget Line | Annual Budget | Planned Cumulative Budget to Date | Actual Cumulative Expenditure to Date | Variance ($) | Variance (%) | Current Month Expenditure | Avg. Monthly Burn Rate | Projected Annual Expenditure | Months Remaining | RAG
Personnel & HR | 18000000 | 7500000 | 7275000 | -225000 | -3% | 1455000 | 1455000 | 17460000 | 7 | On Track
Technical / Program Activities | 9000000 | 3750000 | 3637500 | -112500 | -3% | 727500 | 727500 | 8730000 | 7 | On Track
Equipment, Supplies & Commodities | 7500000 | 3125000 | 3031250 | -93750 | -3% | 606250 | 606250 | 7275000 | 7 | On Track
Training & Capacity Building | 6000000 | 2500000 | 2425000 | -75000 | -3% | 485000 | 485000 | 5820000 | 7 | On Track
Sub-awards / Partner Disbursements | 9500000 | 3958333.3333 | 3839583 | -118750.3333 | -3% | 767917 | 767916.6 | 9214999.2 | 7 | On Track
Monitoring, Evaluation & Learning | 4000000 | 1666666.6667 | 1616667 | -49999.6667 | -3% | 323333 | 323333.4 | 3880000.8 | 7 | On Track
Travel & Transport | 6500000 | 2708333.3333 | 2627083 | -81250.3333 | -3% | 525417 | 525416.6 | 6304999.2 | 7 | On Track
Administration & Overheads | 3000000 | 1250000 | 1212500 | -37500 | -3% | 242500 | 242500 | 2910000 | 7 | On Track
Other Direct Costs / Contingency | 5000000 | 2083333.3333 | 2020833 | -62500.3333 | -3% | 404167 | 404166.6 | 4849999.2 | 7 | On Track
TOTAL PROJECT BUDGET | 68500000 | 28541666.6667 | 27685416 | -856250.6667 | -3% | 5537084 | 5537083.2 | 66444998.4 | 7 | On Track
Planned cumulative budget assumes even (straight-line) spend across the project duration. Variance >20% in either direction triggers Off Track — overspend risks a funding gap; underspend risks an end-of-award absorption/refund issue.
SECTION B · TECHNICAL / DONOR INDICATOR PERFORMANCE
Indicator | Unit / Definition | Annual Target | Planned Cumulative Target to Date | Actual Cumulative Result to Date | Achievement (%) |  |  |  |  | RAG
Tracer Indicator 1 | Define per donor M&E framework | 1200 | 500 | 440 | 88% |  |  |  |  | Watch
Tracer Indicator 2 | Define per donor M&E framework | 600 | 250 | 220 | 88% |  |  |  |  | Watch
Tracer Indicator 3 | Define per donor M&E framework | 900 | 375 | 330 | 88% |  |  |  |  | Watch
Tracer Indicator 4 | Define per donor M&E framework | 450 | 187.5 | 165 | 88% |  |  |  |  | Watch
Tracer Indicator 5 | Define per donor M&E framework | 1500 | 625 | 550 | 88% |  |  |  |  | Watch
Tracer Indicator 6 | Define per donor M&E framework | 300 | 125 | 110 | 88% |  |  |  |  | Watch
Tracer Indicator 7 | Define per donor M&E framework | 750 | 312.5 | 275 | 88% |  |  |  |  | Watch
Tracer Indicator 8 | Define per donor M&E framework | 200 | 83.3333 | 73 | 87.6% |  |  |  |  | Watch
Indicator names are standard/illustrative donor indicators for this project type — replace with your specific donor's exact indicator list, definitions and reporting frequency where they differ.
SECTION C · OVERALL PROJECT HEALTH
Financial RAG (Total Budget): |  |  | On Track | Off-Track Budget Lines: |  |  |  | 0 of 9
Technical RAG (Indicator Performance): |  |  | Watch | Off-Track Indicators: |  |  |  | 0 of 8
OVERALL PROJECT HEALTH: |  |  | Watch
Programme Manager's Narrative — key achievements, bottlenecks, and corrective actions this month:
Type narrative here...

## BFTW RMNCAH
BFTW - RMNCAH Monthly Performance Monitoring
Donor: | Bread for the World |  | Reporting Month: |  | 2026-06-29 |  | Project Duration (months): |  | 12
Project Code: | CHAK/2026/06 |  | Reporting Period: |  | Type reporting period here... |  | Months Elapsed to Date: |  | 5
SECTION A · FINANCIAL PERFORMANCE — BURN RATE & BUDGET VS. ACTUAL (BVA)
Budget Line | Annual Budget | Planned Cumulative Budget to Date | Actual Cumulative Expenditure to Date | Variance ($) | Variance (%) | Current Month Expenditure | Avg. Monthly Burn Rate | Projected Annual Expenditure | Months Remaining | RAG
Personnel & HR | 18000000 | 7500000 | 7875000 | 375000 | 5% | 1575000 | 1575000 | 18900000 | 7 | On Track
Technical / Program Activities | 9000000 | 3750000 | 3937500 | 187500 | 5% | 787500 | 787500 | 9450000 | 7 | On Track
Equipment, Supplies & Commodities | 7500000 | 3125000 | 3281250 | 156250 | 5% | 656250 | 656250 | 7875000 | 7 | On Track
Training & Capacity Building | 6000000 | 2500000 | 2625000 | 125000 | 5% | 525000 | 525000 | 6300000 | 7 | On Track
Sub-awards / Partner Disbursements | 9500000 | 3958333.3333 | 4156250 | 197916.6667 | 5% | 831250 | 831250 | 9975000 | 7 | On Track
Monitoring, Evaluation & Learning | 4000000 | 1666666.6667 | 1750000 | 83333.3333 | 5% | 350000 | 350000 | 4200000 | 7 | On Track
Travel & Transport | 6500000 | 2708333.3333 | 2843750 | 135416.6667 | 5% | 568750 | 568750 | 6825000 | 7 | On Track
Administration & Overheads | 3000000 | 1250000 | 1312500 | 62500 | 5% | 262500 | 262500 | 3150000 | 7 | On Track
Other Direct Costs / Contingency | 5000000 | 2083333.3333 | 2187500 | 104166.6667 | 5% | 437500 | 437500 | 5250000 | 7 | On Track
TOTAL PROJECT BUDGET | 68500000 | 28541666.6667 | 29968750 | 1427083.3333 | 5% | 5993750 | 5993750 | 71925000 | 7 | On Track
Planned cumulative budget assumes even (straight-line) spend across the project duration. Variance >20% in either direction triggers Off Track — overspend risks a funding gap; underspend risks an end-of-award absorption/refund issue.
SECTION B · TECHNICAL / DONOR INDICATOR PERFORMANCE
Indicator | Unit / Definition | Annual Target | Planned Cumulative Target to Date | Actual Cumulative Result to Date | Achievement (%) |  |  |  |  | RAG
Tracer Indicator 1 | Define per donor M&E framework | 1200 | 500 | 465 | 93% |  |  |  |  | On Track
Tracer Indicator 2 | Define per donor M&E framework | 600 | 250 | 232 | 92.8% |  |  |  |  | On Track
Tracer Indicator 3 | Define per donor M&E framework | 900 | 375 | 349 | 93.07% |  |  |  |  | On Track
Tracer Indicator 4 | Define per donor M&E framework | 450 | 187.5 | 174 | 92.8% |  |  |  |  | On Track
Tracer Indicator 5 | Define per donor M&E framework | 1500 | 625 | 581 | 92.96% |  |  |  |  | On Track
Tracer Indicator 6 | Define per donor M&E framework | 300 | 125 | 116 | 92.8% |  |  |  |  | On Track
Tracer Indicator 7 | Define per donor M&E framework | 750 | 312.5 | 291 | 93.12% |  |  |  |  | On Track
Tracer Indicator 8 | Define per donor M&E framework | 200 | 83.3333 | 78 | 93.6% |  |  |  |  | On Track
Indicator names are standard/illustrative donor indicators for this project type — replace with your specific donor's exact indicator list, definitions and reporting frequency where they differ.
SECTION C · OVERALL PROJECT HEALTH
Financial RAG (Total Budget): |  |  | On Track | Off-Track Budget Lines: |  |  |  | 0 of 9
Technical RAG (Indicator Performance): |  |  | On Track | Off-Track Indicators: |  |  |  | 0 of 8
OVERALL PROJECT HEALTH: |  |  | On Track
Programme Manager's Narrative — key achievements, bottlenecks, and corrective actions this month:
Type narrative here...

## PEP
Partnership for Education of Health Professionals (PEP) Monthly Performance Monitoring
Donor: | Novo Nordisk Foundation (NNF) |  | Reporting Month: |  | 2026-06-29 |  | Project Duration (months): |  | 18
Project Code: | CHAK/2026/07 |  | Reporting Period: |  | Type reporting period here... |  | Months Elapsed to Date: |  | 4
SECTION A · FINANCIAL PERFORMANCE — BURN RATE & BUDGET VS. ACTUAL (BVA)
Budget Line | Annual Budget | Planned Cumulative Budget to Date | Actual Cumulative Expenditure to Date | Variance ($) | Variance (%) | Current Month Expenditure | Avg. Monthly Burn Rate | Projected Annual Expenditure | Months Remaining | RAG
Personnel & HR | 18000000 | 4000000 | 3120000 | -880000 | -22% | 780000 | 780000 | 14040000 | 14 | Off Track
Technical / Program Activities | 9000000 | 2000000 | 1560000 | -440000 | -22% | 390000 | 390000 | 7020000 | 14 | Off Track
Equipment, Supplies & Commodities | 7500000 | 1666666.6667 | 1300000 | -366666.6667 | -22% | 325000 | 325000 | 5850000 | 14 | Off Track
Training & Capacity Building | 6000000 | 1333333.3333 | 1040000 | -293333.3333 | -22% | 260000 | 260000 | 4680000 | 14 | Off Track
Sub-awards / Partner Disbursements | 9500000 | 2111111.1111 | 1646667 | -464444.1111 | -22% | 411667 | 411666.75 | 7410001.5 | 14 | Off Track
Monitoring, Evaluation & Learning | 4000000 | 888888.8889 | 693333 | -195555.8889 | -22% | 173333 | 173333.25 | 3119998.5 | 14 | Off Track
Travel & Transport | 6500000 | 1444444.4444 | 1126667 | -317777.4444 | -22% | 281667 | 281666.75 | 5070001.5 | 14 | Off Track
Administration & Overheads | 3000000 | 666666.6667 | 520000 | -146666.6667 | -22% | 130000 | 130000 | 2340000 | 14 | Off Track
Other Direct Costs / Contingency | 5000000 | 1111111.1111 | 866667 | -244444.1111 | -22% | 216667 | 216666.75 | 3900001.5 | 14 | Off Track
TOTAL PROJECT BUDGET | 68500000 | 15222222.2222 | 11873334 | -3348888.2222 | -22% | 2968334 | 2968333.5 | 53430003 | 14 | Off Track
Planned cumulative budget assumes even (straight-line) spend across the project duration. Variance >20% in either direction triggers Off Track — overspend risks a funding gap; underspend risks an end-of-award absorption/refund issue.
SECTION B · TECHNICAL / DONOR INDICATOR PERFORMANCE
Indicator | Unit / Definition | Annual Target | Planned Cumulative Target to Date | Actual Cumulative Result to Date | Achievement (%) |  |  |  |  | RAG
Tracer Indicator 1 | Define per donor M&E framework | 1200 | 266.6667 | 259 | 97.12% |  |  |  |  | On Track
Tracer Indicator 2 | Define per donor M&E framework | 600 | 133.3333 | 129 | 96.75% |  |  |  |  | On Track
Tracer Indicator 3 | Define per donor M&E framework | 900 | 200 | 194 | 97% |  |  |  |  | On Track
Tracer Indicator 4 | Define per donor M&E framework | 450 | 100 | 97 | 97% |  |  |  |  | On Track
Tracer Indicator 5 | Define per donor M&E framework | 1500 | 333.3333 | 323 | 96.9% |  |  |  |  | On Track
Tracer Indicator 6 | Define per donor M&E framework | 300 | 66.6667 | 65 | 97.5% |  |  |  |  | On Track
Tracer Indicator 7 | Define per donor M&E framework | 750 | 166.6667 | 162 | 97.2% |  |  |  |  | On Track
Tracer Indicator 8 | Define per donor M&E framework | 200 | 44.4444 | 43 | 96.75% |  |  |  |  | On Track
Indicator names are standard/illustrative donor indicators for this project type — replace with your specific donor's exact indicator list, definitions and reporting frequency where they differ.
SECTION C · OVERALL PROJECT HEALTH
Financial RAG (Total Budget): |  |  | Off Track | Off-Track Budget Lines: |  |  |  | 9 of 9
Technical RAG (Indicator Performance): |  |  | On Track | Off-Track Indicators: |  |  |  | 0 of 8
OVERALL PROJECT HEALTH: |  |  | Off Track
Programme Manager's Narrative — key achievements, bottlenecks, and corrective actions this month:
Type narrative here...

## GF-MNCH
Gates Foundation MNCH Project Monthly Performance Monitoring
Donor: | Bill & Melinda Gates Foundation |  | Reporting Month: |  | 2026-06-29 |  | Project Duration (months): |  | 12
Project Code: | CHAK/2026/08 |  | Reporting Period: |  | Type reporting period here... |  | Months Elapsed to Date: |  | 6
SECTION A · FINANCIAL PERFORMANCE — BURN RATE & BUDGET VS. ACTUAL (BVA)
Budget Line | Annual Budget | Planned Cumulative Budget to Date | Actual Cumulative Expenditure to Date | Variance ($) | Variance (%) | Current Month Expenditure | Avg. Monthly Burn Rate | Projected Annual Expenditure | Months Remaining | RAG
Personnel & HR | 18000000 | 9000000 | 9090000 | 90000 | 1% | 1515000 | 1515000 | 18180000 | 6 | On Track
Technical / Program Activities | 9000000 | 4500000 | 4545000 | 45000 | 1% | 757500 | 757500 | 9090000 | 6 | On Track
Equipment, Supplies & Commodities | 7500000 | 3750000 | 3787500 | 37500 | 1% | 631250 | 631250 | 7575000 | 6 | On Track
Training & Capacity Building | 6000000 | 3000000 | 3030000 | 30000 | 1% | 505000 | 505000 | 6060000 | 6 | On Track
Sub-awards / Partner Disbursements | 9500000 | 4750000 | 4797500 | 47500 | 1% | 799583 | 799583.3333 | 9595000 | 6 | On Track
Monitoring, Evaluation & Learning | 4000000 | 2000000 | 2020000 | 20000 | 1% | 336667 | 336666.6667 | 4040000 | 6 | On Track
Travel & Transport | 6500000 | 3250000 | 3282500 | 32500 | 1% | 547083 | 547083.3333 | 6565000 | 6 | On Track
Administration & Overheads | 3000000 | 1500000 | 1515000 | 15000 | 1% | 252500 | 252500 | 3030000 | 6 | On Track
Other Direct Costs / Contingency | 5000000 | 2500000 | 2525000 | 25000 | 1% | 420833 | 420833.3333 | 5050000 | 6 | On Track
TOTAL PROJECT BUDGET | 68500000 | 34250000 | 34592500 | 342500 | 1% | 5765416 | 5765416.6667 | 69185000 | 6 | On Track
Planned cumulative budget assumes even (straight-line) spend across the project duration. Variance >20% in either direction triggers Off Track — overspend risks a funding gap; underspend risks an end-of-award absorption/refund issue.
SECTION B · TECHNICAL / DONOR INDICATOR PERFORMANCE
Indicator | Unit / Definition | Annual Target | Planned Cumulative Target to Date | Actual Cumulative Result to Date | Achievement (%) |  |  |  |  | RAG
Tracer Indicator 1 | Define per donor M&E framework | 1200 | 600 | 546 | 91% |  |  |  |  | On Track
Tracer Indicator 2 | Define per donor M&E framework | 600 | 300 | 273 | 91% |  |  |  |  | On Track
Tracer Indicator 3 | Define per donor M&E framework | 900 | 450 | 410 | 91.11% |  |  |  |  | On Track
Tracer Indicator 4 | Define per donor M&E framework | 450 | 225 | 205 | 91.11% |  |  |  |  | On Track
Tracer Indicator 5 | Define per donor M&E framework | 1500 | 750 | 682 | 90.93% |  |  |  |  | On Track
Tracer Indicator 6 | Define per donor M&E framework | 300 | 150 | 136 | 90.67% |  |  |  |  | On Track
Tracer Indicator 7 | Define per donor M&E framework | 750 | 375 | 341 | 90.93% |  |  |  |  | On Track
Tracer Indicator 8 | Define per donor M&E framework | 200 | 100 | 91 | 91% |  |  |  |  | On Track
Indicator names are standard/illustrative donor indicators for this project type — replace with your specific donor's exact indicator list, definitions and reporting frequency where they differ.
SECTION C · OVERALL PROJECT HEALTH
Financial RAG (Total Budget): |  |  | On Track | Off-Track Budget Lines: |  |  |  | 0 of 9
Technical RAG (Indicator Performance): |  |  | On Track | Off-Track Indicators: |  |  |  | 0 of 8
OVERALL PROJECT HEALTH: |  |  | On Track
Programme Manager's Narrative — key achievements, bottlenecks, and corrective actions this month:
Type narrative here...

## IMPACT
IMPACT Project Monthly Performance Monitoring
Donor: | action medeor |  | Reporting Month: |  | 2026-06-29 |  | Project Duration (months): |  | 12
Project Code: | CHAK/2026/09 |  | Reporting Period: |  | Type reporting period here... |  | Months Elapsed to Date: |  | 7
SECTION A · FINANCIAL PERFORMANCE — BURN RATE & BUDGET VS. ACTUAL (BVA)
Budget Line | Annual Budget | Planned Cumulative Budget to Date | Actual Cumulative Expenditure to Date | Variance ($) | Variance (%) | Current Month Expenditure | Avg. Monthly Burn Rate | Projected Annual Expenditure | Months Remaining | RAG
Personnel & HR | 18000000 | 10500000 | 13650000 | 3150000 | 30% | 1950000 | 1950000 | 23400000 | 5 | Off Track
Technical / Program Activities | 9000000 | 5250000 | 6825000 | 1575000 | 30% | 975000 | 975000 | 11700000 | 5 | Off Track
Equipment, Supplies & Commodities | 7500000 | 4375000 | 5687500 | 1312500 | 30% | 812500 | 812500 | 9750000 | 5 | Off Track
Training & Capacity Building | 6000000 | 3500000 | 4550000 | 1050000 | 30% | 650000 | 650000 | 7800000 | 5 | Off Track
Sub-awards / Partner Disbursements | 9500000 | 5541666.6667 | 7204167 | 1662500.3333 | 30% | 1029167 | 1029166.7143 | 12350000.5714 | 5 | Off Track
Monitoring, Evaluation & Learning | 4000000 | 2333333.3333 | 3033333 | 699999.6667 | 30% | 433333 | 433333.2857 | 5199999.4286 | 5 | Off Track
Travel & Transport | 6500000 | 3791666.6667 | 4929167 | 1137500.3333 | 30% | 704167 | 704166.7143 | 8450000.5714 | 5 | Off Track
Administration & Overheads | 3000000 | 1750000 | 2275000 | 525000 | 30% | 325000 | 325000 | 3900000 | 5 | Off Track
Other Direct Costs / Contingency | 5000000 | 2916666.6667 | 3791667 | 875000.3333 | 30% | 541667 | 541666.7143 | 6500000.5714 | 5 | Off Track
TOTAL PROJECT BUDGET | 68500000 | 39958333.3333 | 51945834 | 11987500.6667 | 30% | 7420834 | 7420833.4286 | 89050001.1429 | 5 | Off Track
Planned cumulative budget assumes even (straight-line) spend across the project duration. Variance >20% in either direction triggers Off Track — overspend risks a funding gap; underspend risks an end-of-award absorption/refund issue.
SECTION B · TECHNICAL / DONOR INDICATOR PERFORMANCE
Indicator | Unit / Definition | Annual Target | Planned Cumulative Target to Date | Actual Cumulative Result to Date | Achievement (%) |  |  |  |  | RAG
Tracer Indicator 1 | Define per donor M&E framework | 1200 | 700 | 455 | 65% |  |  |  |  | Off Track
Tracer Indicator 2 | Define per donor M&E framework | 600 | 350 | 228 | 65.14% |  |  |  |  | Off Track
Tracer Indicator 3 | Define per donor M&E framework | 900 | 525 | 341 | 64.95% |  |  |  |  | Off Track
Tracer Indicator 4 | Define per donor M&E framework | 450 | 262.5 | 171 | 65.14% |  |  |  |  | Off Track
Tracer Indicator 5 | Define per donor M&E framework | 1500 | 875 | 569 | 65.03% |  |  |  |  | Off Track
Tracer Indicator 6 | Define per donor M&E framework | 300 | 175 | 114 | 65.14% |  |  |  |  | Off Track
Tracer Indicator 7 | Define per donor M&E framework | 750 | 437.5 | 284 | 64.91% |  |  |  |  | Off Track
Tracer Indicator 8 | Define per donor M&E framework | 200 | 116.6667 | 76 | 65.14% |  |  |  |  | Off Track
Indicator names are standard/illustrative donor indicators for this project type — replace with your specific donor's exact indicator list, definitions and reporting frequency where they differ.
SECTION C · OVERALL PROJECT HEALTH
Financial RAG (Total Budget): |  |  | Off Track | Off-Track Budget Lines: |  |  |  | 9 of 9
Technical RAG (Indicator Performance): |  |  | Off Track | Off-Track Indicators: |  |  |  | 8 of 8
OVERALL PROJECT HEALTH: |  |  | Off Track
Programme Manager's Narrative — key achievements, bottlenecks, and corrective actions this month:
Type narrative here...

## CDIC-iCARE
CDIC / iCARE Program Monthly Performance Monitoring
Donor: | CDC / iCARE |  | Reporting Month: |  | 2026-06-29 |  | Project Duration (months): |  | 6
Project Code: | CHAK/2026/10 |  | Reporting Period: |  | Type reporting period here... |  | Months Elapsed to Date: |  | 2
SECTION A · FINANCIAL PERFORMANCE — BURN RATE & BUDGET VS. ACTUAL (BVA)
Budget Line | Annual Budget | Planned Cumulative Budget to Date | Actual Cumulative Expenditure to Date | Variance ($) | Variance (%) | Current Month Expenditure | Avg. Monthly Burn Rate | Projected Annual Expenditure | Months Remaining | RAG
Personnel & HR | 18000000 | 6000000 | 6480000 | 480000 | 8% | 3240000 | 3240000 | 19440000 | 4 | On Track
Technical / Program Activities | 9000000 | 3000000 | 3240000 | 240000 | 8% | 1620000 | 1620000 | 9720000 | 4 | On Track
Equipment, Supplies & Commodities | 7500000 | 2500000 | 2700000 | 200000 | 8% | 1350000 | 1350000 | 8100000 | 4 | On Track
Training & Capacity Building | 6000000 | 2000000 | 2160000 | 160000 | 8% | 1080000 | 1080000 | 6480000 | 4 | On Track
Sub-awards / Partner Disbursements | 9500000 | 3166666.6667 | 3420000 | 253333.3333 | 8% | 1710000 | 1710000 | 10260000 | 4 | On Track
Monitoring, Evaluation & Learning | 4000000 | 1333333.3333 | 1440000 | 106666.6667 | 8% | 720000 | 720000 | 4320000 | 4 | On Track
Travel & Transport | 6500000 | 2166666.6667 | 2340000 | 173333.3333 | 8% | 1170000 | 1170000 | 7020000 | 4 | On Track
Administration & Overheads | 3000000 | 1000000 | 1080000 | 80000 | 8% | 540000 | 540000 | 3240000 | 4 | On Track
Other Direct Costs / Contingency | 5000000 | 1666666.6667 | 1800000 | 133333.3333 | 8% | 900000 | 900000 | 5400000 | 4 | On Track
TOTAL PROJECT BUDGET | 68500000 | 22833333.3333 | 24660000 | 1826666.6667 | 8% | 12330000 | 12330000 | 73980000 | 4 | On Track
Planned cumulative budget assumes even (straight-line) spend across the project duration. Variance >20% in either direction triggers Off Track — overspend risks a funding gap; underspend risks an end-of-award absorption/refund issue.
SECTION B · TECHNICAL / DONOR INDICATOR PERFORMANCE
Indicator | Unit / Definition | Annual Target | Planned Cumulative Target to Date | Actual Cumulative Result to Date | Achievement (%) |  |  |  |  | RAG
Tracer Indicator 1 | Define per donor M&E framework | 1200 | 400 | 312 | 78% |  |  |  |  | Watch
Tracer Indicator 2 | Define per donor M&E framework | 600 | 200 | 156 | 78% |  |  |  |  | Watch
Tracer Indicator 3 | Define per donor M&E framework | 900 | 300 | 234 | 78% |  |  |  |  | Watch
Tracer Indicator 4 | Define per donor M&E framework | 450 | 150 | 117 | 78% |  |  |  |  | Watch
Tracer Indicator 5 | Define per donor M&E framework | 1500 | 500 | 390 | 78% |  |  |  |  | Watch
Tracer Indicator 6 | Define per donor M&E framework | 300 | 100 | 78 | 78% |  |  |  |  | Watch
Tracer Indicator 7 | Define per donor M&E framework | 750 | 250 | 195 | 78% |  |  |  |  | Watch
Tracer Indicator 8 | Define per donor M&E framework | 200 | 66.6667 | 52 | 78% |  |  |  |  | Watch
Indicator names are standard/illustrative donor indicators for this project type — replace with your specific donor's exact indicator list, definitions and reporting frequency where they differ.
SECTION C · OVERALL PROJECT HEALTH
Financial RAG (Total Budget): |  |  | On Track | Off-Track Budget Lines: |  |  |  | 0 of 9
Technical RAG (Indicator Performance): |  |  | Watch | Off-Track Indicators: |  |  |  | 0 of 8
OVERALL PROJECT HEALTH: |  |  | Watch
Programme Manager's Narrative — key achievements, bottlenecks, and corrective actions this month:
Type narrative here...